PROJECT TIMELINE

for Virginia School Divisions

6 months			A.	Preliminary Planning:

§22.1-138, Code of

Virginia

- Recognize and define present and long term needs.

- Analyze existing buildings, site requirements, transportation needs, finances and budget, school’s grade structure, joint use of facilities, etc.

- Identify funding source.

- Select site.

- Review VDOE’s Guidelines for School Facilities in Virginia’s Public Schools.

- Notify the Office of Support Services of the planned project in the online School Building Construction and Renovation (SBCR) application located in the Single Sign-on for Web Systems (SSWS) to obtain project numbers.

- Discuss objectives, funding, educational trends, and project schedule within the local community.

- Set RFP for professional services to select architect.

- Prepare timetable for planning and construction.

1 -2 months	B.	Programing

- Prepare education program and goals.

- Translate to architectural program.

- Prepare a cost estimate for budgeting.

- Review and approval by School Board.

2 -4 months			C.	Development of Preliminary Drawings

- Prepare preliminary plans and specifications based on approved architectural program.

- Update cost estimate.

- Review and approval by School Board.

12-18 months			D.	Development of Contract Documents

- Set timetable.

- Develop approved preliminary plans into final working drawings and specifications.

- Review and update cost estimate.

- Review and approval by School Board.

(§ 22.1-140, Code of Virginia) Submit one copy of final drawings (half size preferred) and specifications (bid documents) with the approval letter from the Superintendent and a design statement letter from the project architect including a statement that the plans have been reviewed for building security and crime prevention through building design to the Office of Support Services, Department of Education.

2 -3 months			E.	Contract Administration

- Review state procurement requirements.

- Receive and analyze bids

- Execute contract and bonds.

- Provide for adequate supervision of construction.

18 – 36 months		F.	Execution of Construction Contract

- Award of Construction Contract.

- Submit bid cost data with the Office of Support Services, using the School Building Construction and Renovation (SBCR-SSWS) electronic tracking system.

TOTAL TIME			41 – 69 months