Attachment A

Superintendent’s Memo #024-22

January 28, 2022

Attachment A – Projected Timeline for the Review and Revision of the

Mathematics Standards of Learning

September 2019 through November 2021

The Department of Education worked with educators and key stakeholders to explore steps needed to improve and modernize mathematics instruction in the Commonwealth. Additional stakeholder feedback was sought to inform the work of revising the Mathematics Standards of Learning in 2023.

December 2021

The Department of Education prepared for the review process with the creation of public comment feedback forms and collaborated with leadership in creating a timeline and process for submitting public comment on the revision of the 2016 Mathematics Standards of Learning and Curriculum Framework.

January 2022

The Department of Education presents the projected timeline for the review of the 2016 Mathematics Standards of Learning and 2016 Mathematics Standards of Learning Curriculum Framework to the Board of Education. Public comments will be officially solicited from January 27-March 1, 2022.

The Department of Education publishes a Superintendent’s Memorandum that:

- announces the schedule of the review process;

- announces the availability of a review process page posted on the Department of Education’s web site that provides a timeline and procedures for submitting public comment on the 2016 Mathematics Standards of Learning and Curriculum Framework; and

- requests division superintendents share information about the review process page with instructional staff and encourage staff to apply to serve on the 2023 Mathematics Standards of Learning review committee.

The Department of Education posts the review process page on its website that provides a timeline and process for submitting public comment on the 2016 Mathematics Standards of Learning and Curriculum Framework.  The public comment period will be active for no less than 30 days.

March 2022

The Department of Education will convene a Mathematics Education Advisory Committee (MEAC) to review public feedback and support the revision process.

May 2022

Department of Education staff identifies members to serve on the 2023 Mathematics Standards of Learning review committee.

Department of Education staff aggregates and conducts a preliminary analysis of the public comments entered on the webpage.

June 2022

The steering committee (a subset of the 2023 Mathematics Standards of Learning review committee) meets for four days (two days virtually and two days face-to-face) to:

- review and analyze statewide public comment;

- review and select national and international documents and reports necessary to inform the revision process;

- receive training on leading grade-band teams through the standards revision process; and

- make recommendations for potential revisions to the standards.

The review committee meets for six days (two days virtually and four days face-to-face) to:

- review a summary of statewide public comment and analysis of the steering committee;

- review national and international documents and reports selected by the steering committee; and

- make recommendations for potential revisions to the standards and curriculum framework.

July-October 2022

Department of Education staff prepare a draft of the proposed 2023 Mathematics Standards of Learning based upon the work of the steering and review committees.

November 2022

The Department of Education shares a draft of the proposed 2023 Mathematics Standards of Learning with mathematicians and mathematics educators in institutions of higher education across Virginia and professional organizations that focus on mathematics education for review and comment.

The Department of Education shares a draft of the proposed 2023 Mathematics Standards of Learning with representatives of the business community for review and comment.

The Department of Education meets with the Mathematics Education Advisory Committee (MEAC) to seek feedback on the draft of the proposed 2023 Mathematics Standards of Learning.

January 2023

Department of Education staff and the steering committee review comments from higher education staff and business community representatives on the proposed 2023 Mathematics Standards of Learning and make revisions.

March 2023

The Department of Education presents the draft of the proposed 2023 Mathematics Standards of Learning to the Board of Education for first review.

A Superintendent’s Memorandum announces the schedule for public hearings and process for submitting public comment on the proposed 2023 Mathematics Standards of Learning. The public comment period will be active for 30 days.

April 2023

Public hearings held as prescribed by the Board of Education.

Department of Education staff reviews statewide public comment and make edits, as necessary.

September 2023

The Superintendent of Public Instruction presents the proposed 2023 Mathematics Standards of Learning to the Board of Education for final review and adoption.

The Department of Education posts the final documents on its website.

2023-2024 School Year

Department of Education staff provides a crosswalk between the 2016 Mathematics Standards of Learning.

School divisions incorporate the new standards into local written curricula for inclusion in the taught curricula during the 2024-2025 school year.

2024-2025 School Year

Crosswalk year:  2016 Mathematics Standards of Learning and 2023 Mathematics Standards of Learning included in the written and taught curricula.

Standards of Learning assessments in spring 2025 measure the 2016 Mathematics Standards of Learning and include field test items measuring the 2023 Mathematics Standards of Learning.

2025-2026 School Year

Full-implementation year:  Written and taught curricula reflect the 2023 Mathematics Standards of Learning.

Standards of Learning assessments measure the 2023 Mathematics Standards of Learning.